## Gantchart
Project Title
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
Project Title |  | Developing AI Based Comprehensive Framework For Online Assessment |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | Information Technology
Guide |  | Prof. Vishal Badgujar |  |  |  |  | DATE | [6 empty] | 2022-06-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Swapnil, Kunal, Keval | 2021-08-02 | 22/2/21 | 2 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Swapnil , Kunal, Keval | 24/4/21 | 2021-08-05 | 2 | 100% | bar: WEEK 2 W
1.2 | Project Title | Swapnil, Kunal , Keval | 2021-03-05 | 2021-09-05 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Kunal | 2021-11-05 | 16/5/21 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Swapnil | 2021-11-05 | 16/5/21 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Kunal,Keval | 2021-12-05 | 16/5/21 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Swapnil,Kunal,Keval | 20/06/21 | 29/06/21 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Swapnil | 20/06/21 | 23/06/21 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Swapnil,Kunal , Keval | 25/06/21 | 2021-10-07 | 2 | 100% | bar: WEEK 3 F
1.9 | Benefits for environment | Swapnil,Kunal | 2021-12-07 | 14/7/21 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Swapnil | 2021-12-07 | 14/07/21 | 1 | 100% | bar: WEEK 3 F
1.11 | Applications | Swapnil , Kunal , Keval | 13/7/21 | 15/07/21 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Swapnil,Kunal ,Keval | 20/07/21 | 30/07/21 | 2 | 100% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Kunal ,Keval | 22/07/21 | 28/07/21 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
3.1 | Login Register Module | Kunal,Keval,Swapnil | 2021-01-08 | 13/08/21 | 2 | 100%
2.3 | Activity Diagram | Keval | 13/08/21 | 15/08/21 | 1 | 100%
2.4 | Use Case Diagram | Swapnil | 13/08/21 | 15/08/21 | 1 | 100%
2.5 | Description Of Use Case | Swapnil | 14/08/21 | 16/08/21 | 1 | 100%
2.6 | Modules | Swapnil , Kunal , Keval | 18/08/21 | 18/08/21 | 1 | 100%
2.6.1 | Login Register Module | Kunal, Keval | 20/08/21 | 21/08/21 | 1 | 100%
2.6.2 | Teacher Dashboard | Swapnil , Kunal | 20/08/21 | 20/08/22 | 1 | 100%
2.6.3 | Student Dashboard | Keval , Kunal | 22/08/21 | 22/08/21 | 1 | 100%
2.6.4 | ML Module | Swapnil , Keval , Kunal | 23/08/21 | 23/08/21 | 1 | 100%
2.7 | Preparation Of Report | Swapnil , Kunal , Keval | 2022-06-04 | 2022-02-05 | 4 | 100%
3 | Project Implementation
3.2 | Teacher Dashboard Module | Swapnil , Kunal | 30/09/21 | 2021-11-10 | 2 | 100%
3.3 | Student Dashboard Module | Keval , Kunal | 15/10/21 | 26/10/21 | 2 | 100%
3.4 | ML module | Swapnil , Kunal , Keval | 2021-02-11 | 13/11/21 | 2 | 100%
4 | Testing
4.1 | Design of Test Cases | Swapnil, keval | 2022-08-02 | 2022-11-02 | 3 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 | Login - Register Testing | Swapnil,Kunal | 2022-12-02 | 13/2/22 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.3 | Create Exam Testing | Swapnil | 13/2/22 | 15/2/22 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.4 | View/Update/Add Question Testing | Kunal,Keval | 16/2/22 | 17/2/22 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.5 | Attempt Exam Testing | Kunal,Keval | 19/2/22 | 22/2/22 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.6 | Log Generation Testing | Swapnil | 24/2/22 | 27/2/22 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.7 | Student Result generation Testing | Swapni,Keval | 2022-03-03 | 2022-06-03 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F
4.8 | Regenerate secret password Testing | Swapnil | 2022-08-03 | 2020-05-18 | 1 | 100% | bar: WEEK 1 T to WEEK 1 F